Permits & Approvals Checklist for Renovation of German Old Houses

Renovation work in Germany is governed by building codes (Landesbauordnungen/Musterbauordnung), the federal Gebäudeenergiegesetz (GEG) (superseding EnEV) and related laws (e.g. Baugesetzbuch (BauGB), Denkmalschutzgesetze). Any construction or alteration must comply with these rules. Below we summarize required permits, approvals and documents for common renovation types. Where a permit is not required (verfahrensfrei) we note the legal basis. All citations refer to official regulations or authoritative sources.

Building Permits (Baugenehmigung) and Notices

- Building permit (Bauantrag/Baugenehmigung) – Required for any project that changes the static structure or exterior form of a building. For example, altering load-bearing walls, raising the roof or adding a floor always requires a permit. The legal basis is the state Bauordnung (e.g. § 57 BayBO, Art. 60 LBO, etc.) and the federal BauGB if a land-use plan is involved. The permit is issued by the local Bauaufsichtsbehörde (municipal or district building authority) and must be obtained before any construction worksanier.dekanzleimauss.de. The application (Bauantrag) must include required documents (see below). Failure to obtain a necessary permit is a Schwarzbau (illegal construction).

- Permit-free works (Verfahrensfrei) – Many retrofit activities are explicitly exempt from the building permit requirement. Under most state codes (e.g. § 57 BayBO, § 61 SaarLBO), replacement of existing windows/doors in the same openings, façade re-cladding or painting, and adding insulation to walls or roofs (unless a high-rise) are verfahrensfreigesetze-bayern.degesetze-bayern.de. Likewise, new small solar installations (PV or thermal) up to ~3 m height/9 m length are exemptstmwi.bayern.de. In practice, this means that for typical single-family home renovations like adding roof or wall insulation or swapping windows, no building permit is needed. However, even if permit-free, some jurisdictions require a short notification to the Bauamt before starting (often 2 weeks prior) so that inspectors can check compliancegesetze-bayern.de. (For example, BayBO §57(1)(d–e) explicitly lists “Außenwandbekleidungen einschließlich Wärmedämmung” and “Bedachungen einschließlich Wärmedämmung” as verfahrensfreigesetze-bayern.degesetze-bayern.de.)

- Zoning/plan review – Large projects (e.g. a new floor, garage, significant addition) may also trigger Bauvoranfrage (preliminary approval) if uncertain. Check local Bebauungsplan (municipal development plan) for restrictions (setbacks, height limits). If a permit is required, it must be submitted (usually in triplicate) before constructionkanzleimauss.de, and approved by the Bauamt (often the Landratsamt or city building department).

Energy & Efficiency Requirements (GEG/EnEV)

- Thermal insulation (GEG) – The GEG sets minimum U-values for renovated envelopes (walls, roofs, windows). For any roof or wall insulation upgrade, the contractor must provide a “Erfüllungserklärung” (declaration of compliance) under § 19/36 GEG. In practice, a certified energy consultant or the contractor issues this declaration (forms available from state econ. ministries) to prove the work meets GEG standardsverwaltungsportal.hessen.de. Even if no permit is needed, the renovator must keep this proof. After a substantial modernization (e.g. insulating >20% of external surface or replacing >25% of windows), an Energieausweis (energy performance certificate) must be obtained (by a qualified expert) and kept on recordverwaltungsportal.hessen.de.

- Window/Door U-values – Replacing windows/doors triggers the need to meet GEG U-value limits (Uw). For instance, EnEV/GEG require Uw≤1.3 W/m²K for new windows in existing buildings. This is not a separate permit, but a technical requirement. No new building permit is needed for typical window swaps (see above), but the installer should document compliance (often via product certification).

- Heating and technical systems (GEG) – Changing the heating or ventilation system also requires compliance with GEG (§ 10–11). New boilers must meet the renewables-share rules (e.g. ≥ 65 % renewable by 2045)verbraucherzentrale.de. A contractor’s declaration is also required for any new technical building equipment (heating, cooling) under § 36 GEGverwaltungsportal.hessen.de. Generally, installing or replacing a furnace, heat pump, or solar thermal does not require a building permit unless it involves structural alterations (e.g. cutting floors for ducts). However, safety certificates (e.g. from the Schornsteinfeger) are required to operate any new combustion appliance.

- Energy funding documents (BAFA/KfW) – If the renovation uses federal subsidies (BAFA or KfW), additional documents apply: e.g., a KfW “Nachweis” by an Energieberater, or BAFA checklist. These are not official permits, but are important approvals to claim grants. (For example, KfW efficiency-label certificates require approved calculations; BAFA may require proof of ≥ 1st counselor advice.)

Historic Preservation (Denkmalschutz)

- Denkmalschutz-Genehmigung – For listed (protected) buildings, virtually any exterior or structural work requires separate approval from the Denkmalschutzbehörde (Monument Protection Authority). German Monument Protection Laws (state-level Denkmalschutzgesetze) mandate that owners obtain a Denkmalpflege-Genehmigung for renovations affecting historic character (façade painting, window replacement, roof work, etc.). Notably, even if state building law says “verfahrensfrei,” this does not override monument lawdenkmalpflege-bw.de. As the Baden-Württemberg authority states: “Genehmigungsfreiheit nach Landesbaurecht … ist nicht gleichzeitig auch Genehmigungsfreiheit nach Denkmalrecht”denkmalpflege-bw.de. In practice, one must submit plans to the local Denkmalamt and await clearance before working on protected structures. (Federal GEG § 105 even permits deviations from energy rules for monumentsverwaltungsportal.hessen.de.) Timing: the monument permit must be secured before construction on the historic element begins.

Other Required Documents

For any building application (Bauantrag), standard attachments are requiredkanzleimauss.de:

- Bauantragsformular – official application form.

- Baubeschreibung – description of the planned work.

- Lageplan – site plan (official survey showing existing and proposed structures)sanier.de.

- Bestandspläne – existing building floor plans/elevations.

- Entwurfszeichnungen – new construction drawings (floor plans, sections, elevations).

- Statik – structural calculation by a qualified engineer (for any structural change).

- Brandschutz-, Schallschutz-, Wärmeschutznachweis – proof of fire safety, sound insulation and thermal insulation compliance (as required by LBO and GEG)sanier.dekanzleimauss.de.

- Erschließungsangaben – information on water, sewage, road access, etc.

All these must be signed by a bauvorlageberechtigter Entwurfsverfasser (qualified architect/engineer)kanzleimauss.de. The Bauamt will coordinate any required environmental or neighborhood approvals (e.g. water authority if a well is dug). The permit processing time and deadlines vary by state; typically the permit remains valid 3–5 years after issuance.

Checklist by Renovation Type

Below is a summary table of typical renovation actions and whether permits/documents are required. Legal citations are given for each.

| Renovation Work | Permit/Doc Required | Legal Basis & Notes | Authority (where needed) | Timing |
| --- | --- | --- | --- | --- |
| Roof replacement (same shape) | Building permit: Not required (verfahrensfrei)Denkmalschutz: if listed, yesEnergy proof: GEG U-value compliance and contractor’s declaration; Energieausweis if major modernization. | BayBO §57(1)(e); LBO §61(1)(f) – roof cladding+insulation are exempt. GEG §§ 19/36 require proof of insulation U-value. | Local Bauaufsichtsamt; Denkmalschutzamt (if applicable); Energieberater (for Ausweis). | Permit: before work if required (not for typical replacement); Energy docs: submitted with any permit or kept on file. |
| Insulation upgrade (roof or wall) | Building permit: Not required (verfahrensfrei)Denkmalschutz: if listed, yesEnergy documents: GEG compliance declaration; Energieausweis if >20% of facade insulated. | BayBO §57(1)(d–e); LBO §61(1)(e–f) – wall & roof insulation exempt. GEG (GEG §§ 12–15) mandates U-values. | Bauamt; Denkmalbehörde; Energieberater. | Timing: Permit not needed; energy compliance must be documented before/after (as part of renovation paperwork). |
| Window/Door replacement (same opening) | Building permit: Not required (verfahrensfrei)Denkmalschutz: if listed, yesEnergy requirement: Uw≤1.3 W/m²K (GEG) – documented by installer. Energieausweis if extensive. | BayBO §57(1)(c); LBO §61(1)(d) – windows/doors exempt. GEG Anlage 7 sets Uw max. | Bauamt; Denkmalbehörde; Energy consultant. | Permit: none; Energy/docs: as above. |
| Structural modifications (remove/add walls, add floor) | Building permit: Required (statics change)Denkmalschutz: if listed, yesOther docs: full Bauantrag (see above), including Statik, Baubeschreibung, plans. Energieausweis required (building plus new parts). | LandesbauO (e.g. BayBO §57(1)(b); LBO §61 does not list “tragende Bauteile” as free). BauGB §34 if no plan. | Bauaufsichtsbehörde (municipal/District). | Before construction: Complete Bauantrag and approvals must be in hand. |
| Extension/Addition (e.g. new floor, dormer) | Building permit: Required. (Or Anbau if extends footprint, usually permit by LBO)Denkmalschutz: if listed, yesDocuments: full Bauantrag+Statik+Baubeschreibung+EVP (Energiebedarf), possibly Bauvoranfrage. Neighbor consent may be needed for setbacks. Energieausweis required. | BayBO §57(2)(12)(a); LBO §61: new dwellings/dormers in §57/Aufstockung rules not exempt. | Bauamt (+ Stadtplanungsamt, if applicable) | Before work: Permit/approval needed first (construction must await Baugenehmigung). |
| Heating system update (e.g. new boiler, heat pump) | Building permit: Not required (equipment only); local chimney/fire code rules apply. If changing fuel type or major venting, notify Schornsteinfeger and gas utility. Denkmalschutz: if new flues or visual changes to façade of monument, consult Denkmalamt. Energy rules: GEG §§ 10–11 (≥65% renewables by 2045 for new oil/gas); contractor’s declaration required. | EnEV/GEG (e.g. §36/96: KfW/BAFA require fachliche Nachweise). Feuerungsanlagen-Regeln. | Local Schornsteinfegeramt (for inspection); Energieberater (for documentation). | Notify Schornsteinfeger before first firing. –Compliance proof at time of installation. |
| Solar PV / Wind | Building permit: Exempt if roof-mounted within size limits (≤3 m high, ≤9 m total length); otherwise treated as a roof alteration (permit likely needed if over). For ground-mounted in garden, check local rules (often permit required). Denkmalschutz: require approval for panels on listed buildings. Documents: typically electrical permit from utility. | BayBO §57(2)(9–12), BayBauV §29 – small solar exempt. | Bauamt (for permit if needed); local grid operator (for grid connection). | Notification to building and grid authorities before installation. |

| Sources: State building codes (BayBO, LBO etc.) clearly list which renovations are permit-freegesetze-bayern.degesetze-bayern.de. Industry sources confirm that structural changes (Statik) always trigger Baugenehmigungsanier.de. The GEG mandates contractor declarations for thermal and technical workverwaltungsportal.hessen.de, and energy certificates for major modernizationsverwaltungsportal.hessen.de. Historic building regulations supersede all: “Nur wenn… baurechtliche und denkmalschutzrechtliche Genehmigung vorliegen” may one begin workdenkmalpflege-bw.de. Example Checklists Below are sample checklists for three scenarios. Each table lists the relevant permits/documents, whether they are needed, and the legal basis. Item; Required?; Legal Basis / Comments; Authority; Timing. Building Permit; No; Roof insulation (no change to structure or shape) is verfahrensfrei. If house is in a historic district/listed, see Denkmalschutz.; Local Bauamt; N/A (no permit). Denkmalschutz Approval; If listed: YesNo (if not listed); Renovations on listed buildings always need monument permit. Not required if the house has no protected status.; Denkmalbehörde; Before work (if listed). Contractor’s Declaration; Yes; GEG §36 requires owner/contractor to declare that wall/roof components meet energy laws. (Form “Anlage A GEG-Bestand”).; Contractor/Energieberater; With project docs. Energy Performance Cert.; Yes; For a grundlegende Modernisierung (major renovation) an Energieausweis must be issued (since entire roof insulated).; Certified Energiegutachter; After work (or on sale). Baubeschreibung, Pläne; Not needed; A full Bauantrag is not required (no permit), but a documentation of work is recommended for records.; –; –. Item; Required?; Legal Basis / Comments; Authority; Timing. Building Permit; No; Window replacement and new heating (no structural work) are permit-free. (Large roof or facade changes still free.); Local Bauamt; N/A (no permit). Denkmalschutz Approval; If listed: YesNo (if not listed); All exterior work on protected houses needs Denkmalamt approval.; Denkmalbehörde; Before work (if listed). Contractor’s Declaration; Yes; GEG §36 covers both envelope and technical upgrades; a form must be submitted confirming compliance.; Owner/contractor; With project documents. Energy Performance Cert.; Yes; A fundamental modernization (windows + heating) triggers the need for an Energieausweis.; Certified Energieberater; After renovation. Heating system compliance; Yes; GEG §10–11: New heating must meet renewables quota (e.g. ≥65% by 2045). Consultation certificate (Schornsteinfeger) required.; Schornsteinfeger, Energieberater; Before first use. Item; Required?; Legal Basis / Comments; Authority; Timing. Building Permit; Yes; Adding a floor or dormer alters the building’s structure and silhouette; a full Bauantrag is mandatory.; Bauaufsichtsbehörde; Before construction. Denkmalschutz Approval; Yes (if listed); Any new construction on a protected building needs Denkmal-Genehmigung.; Denkmalbehörde; Before construction. Baubeschreibung, Pläne; Yes; Full documents required: Lageplan, Statik report, architectural drawings, fire/sound/thermal proofs.; Bauamt (for review); With application. Contractor’s Declaration; Yes; GEG proof is needed for new insulated surfaces and tech systems.; Owner/contractor; With application. Energy Performance Cert.; Yes; Any major building extension triggers an Energieausweis requirement.; Certified Energieberater; After construction. Rule ID; Condition; Permit/Doc; Legal Basis; Authority; Timing. R1; Roof replacement (shape unchanged); Building Permit: No; BayBO §57(1)(e) (dach inkl. Dämmung verfahrensfrei); Bauamt; –. R2; Roof replacement (shape changed); Building Permit: Yes; BayBO §57(1)(b) (Änderung trag. Bauteile); Bauaufsichtsbehörde; Before construction. R3; Wall/roof insulation; Building Permit: No; BayBO §57(1)(d–e) (Außenwand/Dach verfahrensfrei); Bauamt; –. R4; Window/door replacement; Building Permit: No; BayBO §57(1)(c) (Fenster/Türen verfahrensfrei); Bauamt; –. R5; Structural modification (walls); Building Permit: Yes; LBO §61/§57 (statics not verfahrensfrei); Bauaufsichtsbehörde; Before construction. R6; Adding a floor (Aufstockung); Building Permit: Yes; BauGB §§34/35; LBO Art.57 (dach height change); Bauaufsichtsbehörde; Before construction. R7; Heating system update; Permit: No (use Schornsteinfegerbescheid); GEG §§10–11; EnEV 2014 §§12–13 (technical req.); Schornsteinfegeramt; Notification. R8; Solar PV ≤3m/9m; Building Permit: No; BayBO Art.57(2) (Solaranlagen bis 3m Höhe frei); Bauamt (notify); –. R9; Solar PV >3m/9m or ground-mounted; Building Permit: Yes; BayBO §57(1) (not listed as frei; treated as roof add); Bauamt; Before installation. R10; Denkmalschutz needed; Denkmal Approval: Yes; State DS-Gesetz; GEG §105 (monument priority); Denkmalbehörde; Before work. R11; Major renovation (≥20% envelope); Energy Certificate: Yes; GEG §16 (fundamental modernisation); Energieberater; After renovation. R12; Any insulation/heating work; Contractor Declaration: Yes; GEG §36/§96 (Nachweis Pflicht); Owner/contractor; As part of project. Admin Importer Note To import these rules into a Django admin panel: - Define a Django model (e.g. RenovationRule) with fields matching the table columns (id, condition, permit, required, legal_basis, authority, timing). - Use the django-import-export library or Django's loaddata fixture system. For example, convert the JSON dataset above into a Django fixture (.json) and run manage.py loaddata. - Alternatively, implement a Django admin command that reads the JSON (as Python dicts) and creates RenovationRule objects. - Ensure the model is registered in admin.py to manage these rules via the GUI. Store citations/legal texts in text fields. If complex logic is needed, consider a JSONField for the checklist items. - This way, administrators can edit the permit checklist and legal references through the Django admin interface. Sources: Authoritative German building codes and guidelines were used, including the Bavarian Building Code (BayBO)gesetze-bayern.degesetze-bayern.de, the Saarland LBOsaarland.de, the Hessian GEG portalverwaltungsportal.hessen.deverwaltungsportal.hessen.deverwaltungsportal.hessen.de, and expert overviewssanier.dedenkmalpflege-bw.de. These confirm which renovations require permits and the relevant statutory authorities. { "scenario": "A", "checklist": [ { "permit": "Building permit (Baugenehmigung)", "required": false, "legal_basis": "BayBO §57(1)(d–e) (roof insulation verfahrensfrei):contentReference[oaicite:62]{index=62}:contentReference[oaicite:63]{index=63}", "authority": "Municipal Bauamt", "timing": "Not required (insulation without structural change)" }, { "permit": "Denkmalschutz approval", "required": "Yes if the house is listed", "legal_basis": "State Denkmalschutzgesetz (and GEG §105 priority rule):contentReference[oaicite:64]{index=64}:contentReference[oaicite:65]{index=65}", "authority": "Local Denkmalamt", "timing": "Before work on any protected building" }, { "permit": "Contractor's declaration (GEG)", "required": true, "legal_basis": "§36 GEG – Declaration of fulfilment for thermal envelope work:contentReference[oaicite:66]{index=66}", "authority": "Building owner/contractor", "timing": "Keep with project documentation" }, { "permit": "Energy certificate (Energieausweis)", "required": true, "legal_basis": "§16 GEG – Required for new construction or major modernization:contentReference[oaicite:67]{index=67}", "authority": "Certified Energieberater", "timing": "After renovation (or for sale/rental)" } ] } { "scenario": "B", "checklist": [ { "permit": "Building permit", "required": false, "legal_basis": "BayBO §57(1)(c–e) (window/door and insulation works verfahrensfrei):contentReference[oaicite:73]{index=73}", "authority": "Municipal Bauamt", "timing": "Not required (non-structural retrofit)" }, { "permit": "Denkmalschutz approval", "required": "Yes if building is listed", "legal_basis": "State Denkmalschutzgesetz (override by GEG §105):contentReference[oaicite:74]{index=74}:contentReference[oaicite:75]{index=75}", "authority": "Local Denkmalamt", "timing": "Before any exterior work on a protected house" }, { "permit": "Contractor's declaration (GEG)", "required": true, "legal_basis": "§36 GEG – Declaration for insulated components and heating equipment:contentReference[oaicite:76]{index=76}", "authority": "Building owner / contractor", "timing": "Part of compliance documentation" }, { "permit": "Energy performance certificate", "required": true, "legal_basis": "§16 GEG – Required for fundamental modernization:contentReference[oaicite:77]{index=77}", "authority": "Certified Energieberater", "timing": "After retrofit (for record/sale)" }, { "permit": "Heating compliance", "required": true, "legal_basis": "§10–11 GEG – New heating quotas for renewables:contentReference[oaicite:78]{index=78}", "authority": "Installer / Schornsteinfeger", "timing": "Proof at installation and first operation" } ] } { "scenario": "C", "checklist": [ { "permit": "Building permit", "required": true, "legal_basis": "BayBO §57 – Structural changes to building require permit:contentReference[oaicite:85]{index=85}", "authority": "Municipal Bauaufsichtsbehörde", "timing": "Submit and obtain approval before any building" }, { "permit": "Denkmalschutz approval", "required": "Yes (if building is listed)", "legal_basis": "State Denkmalschutzgesetz (DE §105 GEG):contentReference[oaicite:86]{index=86}:contentReference[oaicite:87]{index=87}", "authority": "Local Denkmalamt", "timing": "Before work on protected structure" }, { "permit": "Construction documents", "required": true, "legal_basis": "BauVorlVO – Complete Bauantrag requires site plan, description, Statik, plans, etc.:contentReference[oaicite:88]{index=88}", "authority": "Owner/Architect; submitted to Bauamt", "timing": "With building permit application" }, { "permit": "Contractor's declaration (GEG)", "required": true, "legal_basis": "§36 GEG – For insulated elements and HVAC in new building parts:contentReference[oaicite:89]{index=89}", "authority": "Owner/contractor", "timing": "Include with application" }, { "permit": "Energy certificate", "required": true, "legal_basis": "§16 GEG – Required for major renovation/extension:contentReference[oaicite:90]{index=90}", "authority": "Energieberater", "timing": "After construction (for registration/sale)" } ] } [ { "id": "R1", "condition": "Roof replacement without structural change", "permit": "Building Permit", "required": false, "legal_basis": "BayBO §57(1)(e) (roof insulation exempt):contentReference[oaicite:103]{index=103}", "authority": "Local Bauamt", "timing": "Not applicable" }, { "id": "R5", "condition": "Structural modification (load-bearing walls)", "permit": "Building Permit", "required": true, "legal_basis": "LBO §61 (Änderung tragender Bauteile not verfahrensfrei):contentReference[oaicite:104]{index=104}", "authority": "Bauaufsichtsbehörde", "timing": "Before construction" }, { "id": "R10", "condition": "Building is listed (Denkmalschutz)", "permit": "Denkmalschutz Approval", "required": true, "legal_basis": "State Denkmalschutzgesetz; GEG §105 (monument law priority):contentReference[oaicite:105]{index=105}", "authority": "Denkmalbehörde", "timing": "Before renovation" }, { "id": "R11", "condition": "Fundamental energy retrofit", "permit": "Energy Performance Certificate", "required": true, "legal_basis": "GEG §16 (certificate for major modernisation):contentReference[oaicite:106]{index=106}", "authority": "Qualified Energieberater", "timing": "After project (or for sale/rent)" } /* ...additional rules... */ ] |  |  |  |  |
| --- | --- | --- | --- | --- |